## Sheet1
|  |  |  | 2014-01-01 |  | 2014-01-02 |  | 2014-01-03 |  | 2014-01-04 | 2014-01-05
2014-01-06 |  | 2014-01-07 |  | 2014-01-08 |  | 2014-01-09 |  | 2014-01-10 |  | 2014-01-11 | 2014-01-12
2014-01-13 | Organisation of Material | 2014-01-14 | Organisation of Material | 2014-01-15 | Assembly of battery module mechanics | 2014-01-16 | Assembly of battery module mechanics | 2014-01-17 | Assembly of battery module mechanics | 2014-01-18 | 2014-01-19
2014-01-20 | Assembly of measurement installation | 2014-01-21 | Assembly of measurement installation | 2014-01-22 | Assembly of measurement installation | 2014-01-23 | Write Script for Evaluator B | 2014-01-24 | Write Script for Evaluator B | 2014-01-25 | 2014-01-26
2014-01-27 | Write Script for Evaluator B | 2014-01-28 | Write Script for Evaluator B | 2014-01-29 | Write Script for Evaluator B | 2014-01-30 | Write Script for Evaluator B | 2014-01-31 | Write Script for Evaluator B
[10 empty] | 2014-02-01 | 2014-02-02
2014-02-03 | Write Script for Evaluator B | 2014-02-04 | Write Script for Evaluator B | 2014-02-05 | Work into LabView | 2014-02-06 | Work into LabView | 2014-02-07 | Work into LabView | 2014-02-08 | 2014-02-09
2014-02-10 | Work into LabView | 2014-02-11 | Work into LabView | 2014-02-12 | Work into LabView | 2014-02-13 | Work into LabView | 2014-02-14 | Work into LabView | 2014-02-15 | 2014-02-16
2014-02-17 | Setup DMM | 2014-02-18 | Setup DMM | 2014-02-19 | Setup DMM | 2014-02-20 | Setup DMM | 2014-02-21 | Setup DMM | 2014-02-22 | 2014-02-23
2014-02-24 | Setup DMM | 2014-02-25 | Setup DMM | 2014-02-26 | Setup DMM | 2014-02-27 | Setup CAN bus | 2014-02-28 | Setup CAN bus
[10 empty] | 2014-03-01 | 2014-03-02
2014-03-03 | Setup CAN bus | 2014-03-04 | Setup CAN bus | 2014-03-05 | Setup LIN bus | 2014-03-06 | Setup LIN bus | 2014-03-07 | Setup LIN bus | 2014-03-08 | 2014-03-09
2014-03-10 | Setup LIN bus | 2014-03-11 | Setup LIN bus | 2014-03-12 | program the LabVIEW programme | 2014-03-13 | program the LabVIEW programme | 2014-03-14 | program the LabVIEW programme | 2014-03-15 | 2014-03-16
2014-03-17 | program the LabVIEW programme | 2014-03-18 | program the LabVIEW programme | 2014-03-19 | program the LabVIEW programme | 2014-03-20 | program the LabVIEW programme | 2014-03-21 | program the LabVIEW programme | 2014-03-22 | 2014-03-23
2014-03-24 | program the programme for postprocessing | 2014-03-25 | program the programme for postprocessing | 2014-03-26 | program the programme for postprocessing | 2014-03-27 | program the programme for postprocessing | 2014-03-28 | program the programme for postprocessing | 2014-03-29 | 2014-03-30
2014-03-31 | perform verification measurements
|  | 2014-04-01 | perform verification measurements | 2014-04-02 | perform real measurements for LEM
timeline proposal
Task | Net time needed
Organisation of material | 1 | d | 1.6667 | 1.6667 | 2
Assembly of battery module mechanics | 2 | d | 3.3333 | 5 | 5
Assembly of measurement installation (Sensors, supplies, cables) | 2 | d | 3.3333 | 8.3333 | 8
Write Script for Evaluator B to drive current curves | 5 | d | 8.3333 | 16.6667 | 17
Work into LabView | 5 | d | 8.3333 | 25 | 25
Setup DMM and connect to acquire measurements | 5 | d | 8.3333 | 33.3333 | 33
Setup CAN bus and communication | 2 | d | 3.3333 | 36.6667 | 37
Setup LIN bus and communication | 3 | d | 5 | 41.6667 | 42
program the LabVIEW programme to collect the data | 5 | d | 8.3333 | 50 | 50
program the programme for postprocessing | 3 | d | 5 | 55 | 55
perform verification measurements | 1 | d | 1.6667 | 56.6667 | 57
perform real measurements for LEM | 1 | d | 1.6667 | 58.3333 | 58
total net time | 35 | d | 58.3333
capacity utilisation | 0.6
total gross time | 58.3333 | d
| 2.7222 | months