## Sheet1
timeline proposal
Task | Net time needed
Organisation of material | 1 | d
Assembly of battery module mechanics | 2 | d
Assembly of measurement installation (Sensors, supplies, cables) | 2 | d
Write Script for Evaluator B to drive current curves | 5 | d
Work into LabView | 5 | d
Setup DMM and connect to acquire measurements | 5 | d
Setup CAN bus and communication | 2 | d
Setup LIN bus and communication | 3 | d
program the LabVIEW programme to collect the data | 5 | d
program the programme for postprocessing | 3 | d
perform verification measurements | 1 | d
perform real measurements for LEM | 1 | d
total net time | 35 | d
capacity utilisation | 0.6
total gross time | 58.3333 | d
| 2.7222 | months